## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2181-swen-261-10-e-echo10
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | AF, 10/11/2018
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | AF, 10/11/2018
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | AF, 10/11/2018
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | AF, 10/11/2018
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | AF, 10/11/2018, Entering the same username ('as') in incognito mode and in a regular Chrome session accepted both use being a valid name. AF, 10/11/2018
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | AF, 10/11/2018, After successfully signing in, the page still shows a link to sign in and does not display a link to sign out. Additionally, navigating to this 'signin' page under these conditions leads to inconsistent behavior. AF, 10/11/2018
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | AF, 10/11/2018, There is no method provided to navigate to a 'signout' page. AF, 10/11/2018
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | AF, 10/11/2018, When signed in and no other users are present, a blank page is displayed (this is technically correct). It's probably best to display a message that no other users are currently logged In.
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | AF, 10/11/2018
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | SK, 10/12/2018
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | SK, 10/12/2018
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | SK, 10/12/2018
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | SK, 10/12/2018
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | SK, 10/12/2018
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | SK, 10/12/2018
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | SK, 10/12/2018
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | SK, 10/12/2018
As a Player I want to sign-out so I can release my identity. | Given that I am signed in when I view the Home page, then I expect to see a means to sign out. |  |  | Pass | MH, 10/26/2018
| Given that I am signed in when I view the Game page, then I expect to see a means to sign out. |  |  | Pass | MH, 10/26/2018
| Given that I am signed in and I select to sign out when I view the Home page, then I expect to no longer be signed in and for my username to be available for anyone to use. |  |  | Pass | MH, 10/26/2018
| Given that I am signed in and I select to sign out when I view the Game page, then I expect to no longer be signed in and for my username to be available for anyone to use. |  |  | Pass | MH, 10/26/2018
| Given that I am not signed in when I manually force a sign out attempt, then I expect to see the Home page with an appropriate error. |  |  | Pass | MH, 10/26/2018 No error was indicated.
| Given that I am in a game, when I press the Sign Out button, then I automatically resign before signing out. |  |  | Pass | MH, 10/26/2018 Given that a player selects sign out they are returned to the home page as expected, but if they OR another user signs in with the same username they are automatically brought back into their past played game. The Game is not terminated, this is based on the implementation of resign.
As a Player I want to be able to backup a move before submitting it so that I can recover from my numerous mistakes in life. | Given that I've made a valid move and haven't clicked Submit when I select the Backup option, then I expect the move to be reverted. |  |  | Pass | AF, 11/4/2018
| Given that it's my turn and I haven't made a move when I click the Backup button, then I expect nothing to happen. |  |  | Pass | AF, 11/4/2018
| Given that it's not my turn when I click the Backup button, then I expect nothing to happen. |  |  | Pass | AF, 11/4/2018
As a Player I want to be able to move diagonally forward one space so that I can advance across the board. | Given it is my turn when I move a piece to a valid, empty position that is one spot away diagonally, then I expect for the game to accept the move as valid. |  |  | Pass | SK, 11/3/2018
| Given it is my turn when I move a piece to an empty position that is more than one spot away diagonally, then I expect for the game to reject the move. |  |  | Pass | SK, 11/3/2018
As a Player I want to know when it is my turn so I may go forth and slay my enemy. | Given it is my turn when select I select to submit my move, then I expect for the game to progress to my opponent's turn. |  |  | Pass | MH, 11/05/2018
| Given it is not my turn when my opponent submits a move, then I expect for the game to progress to my turn. |  |  | Pass | MH, 11/05/2018
As a Player I want to be able to jump over and capture enemy pieces so I may remove them from the board and advance my way towards victory. | Given it is my turn when I move a piece to a valid, empty position that jumps an opponent's piece, then I expect for the game to accept the move as valid and to remove the jumped piece from play. |  |  |  |  | Pass | SK, 11/10/2018
| Given it is my turn when I move a piece to an invalid position that jumps an opponent's piece, then I expect for the game to reject the move. |  |  |  |  | Pass | SK, 11/10/2018
| Given it is not my turn when my opponent jumps one of my pieces, then I expect to be able to see the move they made. |  |  |  |  | Pass | SK, 11/10/2018
As a Player I want to chain jumps together when possible so that my superior positioning and planning can be rewarded. | Given that a piece can make a multiple-jump move, when I make the first jump in that move, then I may still move. |  |  |  |  | Pass | MH, 11/12/2018 multiple jumps works;however, there are a few errors with moving not related directly to multiple jump. 1) you can make a sequence of simple moves and jumps 2) if you make a simple move next to an opponents checker it forces you to jump their checker 3) method invalid() is not aligning with turn checking methods()
| Given that a piece can make a multiple-jump move when I make the first jump in that move, then I am forced to make the next jump. |  |  |  |  | Pass | MH, 11/12/2018
| Given that I am making a jump move when I have completed all subsequent jumps, then I expect the game to progress when I submit the move. |  |  |  |  | Pass | MH, 11/12/2018
| Given that I am using a single piece to make a jump move when I make a jump move, then I expect the game to only consider valid a jump that progresses towards the opponent's side. |  |  |  |  | Pass | MH, 11/12/2018
As a Player I want to resign at any point in time from a game so that I may surrender with what is left of my dignity. | Given that I am in a game, when I view the game board, then I expect to see a means to resign. |  |  |  |  | Pass | AF 11/22/18
| Given that I am in a game, when I select Resign, then I expect to see a popup confirming my intent to resign. |  |  |  |  | Pass | AF 11/22/18
| Given that I have selected Resign, when I confirm my intent to resign, then I expect to be resigned from the game and returned to the Home page. |  |  |  |  | Pass | AF 11/22/18
| Given that I have selected Resign, when I rescind my intent to resign, then I expect to be returned to the game. |  |  |  |  | Pass | AF 11/22/18
| Given that I am in a game, when I make a move, then I expect the resign button to be disabled until I submit the move. |  |  |  |  | Pass | AF 11/22/18
| Given that I am in a game, when I select Backup, then I expect the resign button to be enabled again. |  |  |  |  | Pass | AF 11/22/18
As a Player I want to know when my opponent has resigned so I may go defeat another champion. | Given that I am in a game when my opponent resigns on their turn then I expect to receive an info message immediately letting me know of their resignation |  |  |  |  | Pass | AF 11/22/18
| Given that I am in a game when my opponent resigns on my turn then I expect to receive an info message after I have submitted my turn letting me know of their resignation |  |  |  |  | Pass | AF 11/22/18
As a Player when my piece reaches the far side of the board I want it to be promoted by my opponent to a King piece so that I can obtain a wider range of movement. | Given that I reach the opponent's side of the board when I make a simple move, then I expect my piece to be converted to a King piece |  |  |  |  | Pass | The piece is promoted on the previous board stored. MH, 11/27/2018
| Given that I reach the opponent's side of the board when I make a jump move, then I expect my piece to be converted to a King piece |  |  |  |  | Pass | The piece is promoted on the previous board stored. MH, 11/27/2018
| Give I am not a king piece when I reach the opponent's side of a board, then I expect my turn to end. |  |  |  |  | Pass | The piece is never able to be checked for current state as it is not updated on the current state of the board. MH, 11/27/2018
| Given I am a king piece when I reach the opponent's side of a board, then I expect to maintain my rank. |  |  |  |  | Pass | The piece is never able to be checked for current state as it is not updated on the current state of the board. MH, 11/27/2018
As a Player I want my king piece to have the option to move diagonally backwards (as well as forwards) so that I can flaunt my superior social status. | Given I am a king piece when it is my turn, then I expect to be able to make a simple move towards my own side. |  |  |  |  | Pass | MH, 11/27/2018
| Given I am a king piece when it is my turn, then I expect to be able to make a single jump move towards my own side. |  |  |  |  | Pass | MH, 11/27/2018
| Given I am a king piece when it is my turn, then I expect to be able to make a multi-jump move towards my own side. |  |  |  |  | Pass | MH, 11/27/2018
As a player, I want to know when all of a player's pieces are captured so that I know when the game is over. | Given that it is my turn when I capture my opponent's last piece then I expect the game to end with a notification stating that I have won, along with the reason for winning. |  |  |  |  | Pass | AF, 11/15/2018
| Given I have no more pieces on the board when my opponent has finished their turn then I expect the game to end with a notification stating that I have lost, along with the reason for losing. |  |  |  |  | Pass | AF, 11/15/2018
As a player, I want to know when a player is unable to move so that I know when the game is over. | Given I am unable to move when it is my turn then I expect the game to end with a message stating that I have lost, along with the reason for losing. |  |  |  |  | Pass | SK, 11/26/2018
| Given my opponent is unable to move when it is their turn then I expect the game to end with a message stating that I have won, along with the reason for winning. |  |  |  |  | Pass | SK, 11/26/2018
As an AI, I want to make random moves in order to show that I can still beat humans without needing to think. | Given I am signed in when I view the home page then I expect to be able to select to play against a random movement AI. |  |  |  |  | Pass | SK, 11/27/2018
| Given I am not signed in when I view the home page then I expect see the number of signed in, non-AI players. |  |  |  |  | Pass | SK, 11/27/2018
| Given I start a game against the AI when I am the red player then I expect to be able to make the first move. |  |  |  |  | Pass | SK, 11/27/2018
| Given my turn is over when I submit my turn then I expect my opponent to make a random move. |  |  |  |  | Pass | SK, 11/27/2018
| Given my opponent has no more forced jumps when they have made a move then I expect the game to progress to my turn. |  |  |  |  | Pass | SK, 11/27/2018
As an AI, I will be able to compute a quality of the current state of the board in order to know how likely I am to win. | Given the board is in a given state when I must look at the board then I expect to be able to calculate the cost of the board relative to my opponent. |  |  |  |  | Pass | SK, 11/27/2018
| Given the board is in a given state when I must look at the board then I expect to be able to look at how a single, valid change would affect the cost of the board relative to me and my opponent. |  |  |  |  | Pass | SK, 11/27/2018
| Given the board is in a given state when I must look at the board then I expect to be able to look at how chained, valid changes would affect the cost of the board relative to me and my opponent. |  |  |  |  | Pass | SK, 11/27/2018
| Given the board is in a given state when I must look at the board then I expect to be able to calculate the cost of the board relative to me. |  |  |  |  | Pass | SK, 11/27/2018
As an AI, I will be able to play at the level of a basic human in order to give humanity false hope for the future. | Given the board is in a given state when I must look at the board then I expect to be able to look at how a single, valid change would affect the cost of the board relative to me and my opponent. |  |  |  |  | Pass | SK, 11/27/2018
| Given the board is in a given state when I must look at the board then I expect to be able to look at how chained, valid changes would affect the cost of the board relative to me and my opponent. |  |  |  |  | Pass | SK, 11/27/2018
| Given my turn is over when I submit my turn then I expect my opponent to make a move that takes into account the current state of the board. |  |  |  |  | Pass | SK, 11/27/2018
As a player, I want to be able to select to start the game with a set number of pieces randomly placed on each side so that I can practice playing from an unknown start state. | Given I am signed in when view the home page, then I expect to be able to choose the starting number of red pieces. |  |  |  |  | Pass | MH, 11/27/2018 The number of pieces choosen for a given selection do not appear.
| Given I am signed in when view the home page, then I expect to be able to choose the starting number of white pieces. |  |  |  |  | Pass | MH, 11/27/2018 The number of pieces choosen for a given selection do not appear.
| Given I am not signed in when view the home page, then I expect to not be able to alter any starting parameters. |  |  |  |  | Pass | MH, 11/27/2018
| Given I start a game when I have selected how many pieces to place on each side, then I expect to enter a game where both sides have the set number of pieces randomly placed on the board. |  |  |  |  | Pass | MH, 11/27/2018 500 error
As a player, I want to be able to select the starting board from a set of boards so that I can practice playing from different game states. | Given I am signed in when view the home page, then I expect to be able to choose to start from the start of a game. |  |  |  |  | Pass | MH, 11/27/2018
| Given I am signed in when view the home page, then I expect to be able to choose to start from around mid-way through a game. |  |  |  |  | Pass | MH, 11/27/2018
| Given I am signed in when view the home page, then I expect to be able to choose to start from towards the end of the game. |  |  |  |  | Pass | MH, 11/27/2018
| Given I am not signed in when view the home page, then I expect to not be able to alter any starting parameters. |  |  |  |  | Pass | MH, 11/27/2018
As a Player I want my opponent to be disqualified from the game if they are away from their keyboard so that I am not endlessly waiting for my turn. | Given I have not made a move in the allotted time when it is my turn then I expect the game to end with a message stating that I have lost, along with the reason for losing.
Given my opponent has not made a move in the allotted time when it is their turn then I expect the game to end with a message stating that I have won, along with the reason for winning.
Given my opponent has not made a move in the allotted time when it is their turn then I expect to receive an info message immediately letting me know that they are AFK.
As a player, I want to be able to select to start the game with a set number of pieces randomly placed on each side so that I can practice playing from an unknown start state. | Given I am signed in when I view the home page, then I expect to be able to choose the starting number of red pieces. |  |  |  |  | Pass | SK, 11/27/2018
| Given I am signed in when view the home page, then I expect to be able to choose the starting number of white pieces. |  |  |  |  | Pass | SK, 11/27/2018
| Given I am not signed in when view the home page, then I expect to not be able to alter any starting parameters. |  |  |  |  | Pass | SK, 11/27/2018
| Given I start a game when I have selected how many pieces to place on each side, then I expect to enter a game where both sides have the set number of pieces randomly placed on the board. |  |  |  |  | Pass | SK, 11/27/2018